## Slide 1
CBSC-16
Eastern Atlantic Hydrographic Commission (EAtHC)
Report to CBSC
GOA, India, 30 May – 1 June 2018

## Slide 2: Activities completed since CBSC15
Technical visit to Gambia
  July 24-28 2017
  Visiting team Shom & UKHO
Training center visit to Nigeria
  March 17-24 2018
  Visiting team Shom & UKHO
Training assistance offered to Nigeria MSI Coordinator (May 14-18 2018). Shom starts to transmit the coastal warnings of Nigeria in the form of NAVAREA II messages (through SafetyNET)

## Slide 3: Activities planned for 2018
Pursue visits to Training centres (Gabon & Cameroun)
Regional awareness seminar on Maritime Geospatial Knowledge (15-16 October)
Pursue the promotion of the HydroMAOC study results
Development of an English version of the MSI E-Learning resource
Development of a E-Learning course on survey specification (with support of CHS - tbc)

## Slide 4: Procedure 11: EAtHC self-assessment
N. | Coastal State/Territory | NHC/NHCC | Phase 1 | Phase 2 | Phase 3 | Last TV | IMSAS
5 | Angola | 0 | 2 | 3 | 3 | 2008 | 2022
19 | Benin | 0 | 3 | 3 | 3 | 2003 | 2020
29 | Cabo Verde | 0 | 2 | 3 | 3 | 2003, 2017 | May 2017
31 | Cameroon | 0 | 2 | 3 | 3 | 2011 | 2020
39 | Congo | 0 | 3 | 3 | 3 | 2003 | 2018
42 | Côte d'Ivoire | 0 | 2 | 3 | 3 |  | Feb 2016
48 | Democratic Republic of the Congo | 0 | 2 | 3 | 3 | 2003 | May 2017
56 | Equatorial Guinea | 0 | 2 | 1 | 3 | 2003 | 2018
62 | France | 2 | 4 | 4 | 4 | N/R | 2021
63 | Gabon | 0 | 1 | 1 | 3 | 2003, 2012 | Apr 2017
64 | Gambia | 0 | 2 | 2 | 3 | 2017 | Feb 2017
67 | Ghana | 2 | 3 | 1 | 3 | 2003 | Jan 2017
71 | Guinea | 1 | 2 | 3 | 3 | 2003 | Jul 2016
72 | Guinea-Bissau | 0 | 2 | 1 | 3 | 2003, 2012 | NA (C113)
98 | Liberia | 0 | 2 | 1 | 3 | 2016 | 2020
110 | Mauritania | 0 | 2 | 3 | 3 | 2003 | Apr 2016
117 | Morocco | 2 | 3 | 4 | 3 |  | 2022
127 | Nigeria | 1 | 2 | 4 | 3 | 2003 2018 (training centers visit) | Jun 2016
139 | Portugal | 2 | 4 | 4 | 4 | N/R | Apr 2016
151 | Sao Tome and Principe | 0 | 3 | 3 | 3 |  | 2018
153 | Senegal | 2 | 3 | 3 | 3 | 2003 | Jul 2016
156 | Sierra Leone | 0 | 2 | 1 | 3 | 2003 | 2018
164 | Spain | 2 | 4 | 4 | 4 | N/R | 2020
177 | Togo | 2 | 3 | 3 | 3 | 2003 | Feb 2016
187 | United Kingdom | 2 | 4 | 4 | 4 | N/R | 2020
189 | United States of America | 2 | 4 | 4 | 4 | N/R | 2021

## Slide 5: Procedure 11: EAtHC self-assessment
N. | Coastal State/Territory | NHC/NHCC | Phase 1 | Phase 2 | Phase 3 | Last TV | IMSAS
5 | Angola | 0 | 2 | 3 | 3 | 2008 | 2022
19 | Benin | 0 | 3 | 3 | 3 | 2003 | 2020
29 | Cabo Verde | 0 | 2 | 3 | 3 | 2003, 2017 | May 2017
31 | Cameroon | 0 | 2 | 3 | 3 | 2011 | 2020
39 | Congo | 0 | 3 | 3 | 3 | 2003 | 2018
42 | Côte d'Ivoire | 0 | 2 | 3 | 3 |  | Feb 2016
48 | Democratic Republic of the Congo | 0 | 2 | 3 | 3 | 2003 | May 2017
56 | Equatorial Guinea | 0 | 2 | 1 | 3 | 2003 | 2018
63 | Gabon | 0 | 1 | 1 | 3 | 2003, 2012 | Apr 2017
64 | Gambia | 0 | 2 | 2 | 3 | 2017 | Feb 2017
67 | Ghana | 2 | 3 | 1 | 3 | 2003 | Jan 2017
71 | Guinea | 1 | 2 | 3 | 3 | 2003 | Jul 2016
72 | Guinea-Bissau | 0 | 2 | 1 | 3 | 2003, 2012 | NA (C113)
98 | Liberia | 0 | 2 | 1 | 3 | 2016 | 2020
110 | Mauritania | 0 | 2 | 3 | 3 | 2003 | Apr 2016
117 | Morocco | 2 | 3 | 4 | 3 |  | 2022
127 | Nigeria | 1 | 2 | 4 | 3 | 2003, 2018 | Jun 2016
151 | Sao Tome and Principe | 0 | 3 | 3 | 3 |  | 2018
153 | Senegal | 2 | 3 | 3 | 3 | 2003 | Jul 2016
156 | Sierra Leone | 0 | 2 | 1 | 3 | 2003 | 2018
177 | Togo | 2 | 3 | 3 | 3 | 2003 | Feb 2016
WCA Coastal States

## Slide 6: CBWP submissions for 2019
4 coastal states answered the questionnaire to collect their requirements in term of CB
  Portugal (IHPT)
  Nigeria (NNHO)
  Gambia (Gambia Ports Authority)
  Gabon (Dir.of the Merchant Navy & NODC – Gabon Port management)
No answer regarding the proposal to conduct risk assessment studies
No feedback received on recent IMSAS

## Slide 7: CBWP submissions for 2019
2019: CB submissions for EAtHC
Based on current implementation of the CB strategy in the EAtHC
Technical visits Congo, Gambia, Togo
E-learning guided session: MSI
E-learning guided session: survey specifications
Pursue regional training center visits
Workshop : MSI, Hydrographic risk assessment & Survey specification
Or a different approach…
 EAtHC 3 years plan 2019-2021: lack of visibility regarding the mid term strategy

## Slide 8: Difficulties encountered and challenges yet to be addressed
Challenges in the WCA sub-region (except Morocco & Nigeria) remain considerable
  Ever-growing needs in term of maritime geospatial knowledge
  Hydrographic services remain very limited
Continuous and specific CB efforts during the last 15 years have lead to very limited progress.

## Slide 9: Achievements/Outputs/Conclusions
Hydrographic capacity development in the EAtHC region remains a real challenge. Considering the magnitude of the task and the available resources, a different implementation of the CB strategy may be considered for this region
See CBS16-06F

## Slide 10: Actions Required of CBSC16
Please note this report
Consider the need for a new approach (see CBSC16-06F)

## Slide 11: Thank You