## Slide 1: IHO CAPACITY BUILDING SUB-COMMITTEE CBSC20 Southern African & Islands Hydrographic Commission (SAIHC) Report to CBSC Bali, Indonesia, 1-3 June 2022 Capacity Building Update
Lucy Fieldhouse

## Slide 2: 1. Activities completed since CBSC19 – 2021WP Review
Activities unable to be completed in 2021 due to the requirement of in person delivery
No. | Event | Status
A-02 | TV Tanzania | See A-03 2022 Workplan
P-09 | MSI Course | Carry into 2022 Workplan. Delivery 17-21 October 2022
P-16 | Raising Hydrography Awareness | Carry into 2022 Workplan. Face to face requirement - Date for delivery 9th May to precede SAIHC18, Maputo, Mozambique
P-25 | ENC Training for Mozambique | Carry into 2022 Workplan. Postponed until 2022 as requested by Portugal who will deliver the training. Date for delivery to be confirmed
P-44 | MSDI Training Course | As P-41 Unfunded in plan but delivered virtually by IHO MSDIWG and UKHO January 2020

## Slide 3: 2. SAIHC 2022 CB Update (funded activities)
Technical Visit to Republic of Tanzania - proposed date 2-8 October
High level and Technical Visit to Comoros
Raising Hydrographic Awareness - preceded the 18th meeting of SAIHC. Addressed SPIs to raise regional awareness of the IHO Strategic plan and its related goals and targets.
MSI Course - Dates for delivery are 17-21 October 2021 - Mauritius.
ENC Training for Mozambique – Portugal are in discussion with Mozambique regarding delivery of this activity.
Notes: Moving onto the IHO funded CB activities that are scheduled this year, as previously said those funded in the recent workplans impacted by COVID will be carried over. Therefore,
Technical Visit to Republic of Tanzania Date for completion to be confirmed
High level and Technical Visit to Comoros FUNDED
Raising Hydrographic Awareness (for SAIHC Associate and Non-Members) FUNDED Completed on the 9 May preceding this 18th meeting of SAIHC. Addressed SPIs to raise regional awareness of the IHO Strategic plan and its related goals and targets. IHO funding enabled the largest attendance of SAIHC to meet in person and virtually. Attendance of Uganda
MSI Course Carried over due to COVID - Dates for delivery are: 17-21 October 2021 Host required. If anyone would like to speak with me about hosting the course please come and speak to me out of session.
ENC Training for Mozambique (from 2021 P-25) FUNDED – Portugal are in discussion with Mozambique regarding delivery of this activity.
High level and Technical Visit to Madagascar Not funded yet (resubmitted on request from Madagascar for consideration 2023)
Introduction to Tides and Water Levels Workshop SAIHC UNFUNDED resubmitted for consideration for funding for 2023

## Slide 4: 3. Regional update
Due to the impact of COVID there has been little capability development in the region since CBSC19 – IHO Funded MSI Course Scheduled.
The development of the SAIHC African Great Lakes and Rivers Working Group (AGL&R WG) has increased in engagement
Work will take place to:
develop a regional CB Programme to identify the resources that are available within the area
Assess the gap analysis work to identify work for the regional CB Workplan
4. Train the Trainer Programme in Basic Hydrography 1-12 November 2021 - Mauritius
Notes: Cl 39/2021 refers to Train the trainer

## Slide 5: 4. SAIHC 2022 – 2024 Workplan - 2023 Proposals
Proposals for 2023 (CBSC20 Jun 1 – 3 2021, Bali, Indonesia).
Technical Visit to Madagascar – Resubmission upon request from Madagascar
Raising Awareness of Hydrography to precede SAIHC19
High Level Technical Visit to Angola
Tides and water levels workshop supported by SANHO
MBES Data collection and processing Course for Angola
Notes: Thank you for your input into the proposals for funding from the IHO for 2023 for the SAIHC region.
Following email correspondence the following proposals were developed and submitted to CBSC and the IHO Secretariat for consideration in April. At the next CBSC meeting, meeting 20 which will be held 1-3 June we will discuss the workplan for 2023 and I will be able to confirm what funding has been secured.
The proposals submitted as requested are:
Technical Visit to Madagascar – unfunded in 2022 workplan and request from Madagascar to resubmit due to the requirement of this activity to assist in their development
Raising Awareness of Hydrography to precede SAIHC19
High Level Technical Visit to Angola – New Member state, requested visit
Tides and water levels workshop supported by SANHO
MBES Data collection and processing Course for Angola – to assist in developing domestic capability in hydrographic data collection and processing.

## Slide 6: 5. SAIHC 2022 – 2024 Workplan - 2024
Proposed activities for 2024 are:
Technical Implementation Visits for identified Coastal States
MBES Processing For identified coastal states (Supporting G1, T1.2 SPI 1.2.2
Awareness Seminar to precede the main SAIHC meeting For identified coastal states
S10X Awareness For identified Coastal States (supporting G1, T1.3 SPI1.3.1
Data Management (supporting G2, T2.3. SPI 2.3.1)

## Slide 7: The CBSC is invited to : 1. Note this report 2. Take any action considered appropriate