## Slide 1: Preparation of HSSC-10 and Council C-2
1
Date | What?
14 Nov 2017 | IHO CL announcing HSSC-10 (T0 – 6 months, iaw HSSC ROPs)
26 March 2018 | Deadline for submission of reports/proposal/new editions…that need decisions (T0- 7 weeks)
Mid-April 2018 | S-100WG3, TWCWG3, ENCWG3
14-18 May 2018 | HSSC-10
9 June 2018 | Circulation of C-2 provisional Agenda
9 July 2018 | Deadline for Submission of proposals to the Secretariat and circulation by the IHO Sec. as soon as they are received (uploaded on Council meeting webpage)
9 Aug 2018 | Circulation of reports (top priorities, risk/issues…) and other documents (among them the Red Book)
9 – 11 Oct 2018 | Council Meeting

## Slide 2: Proposals for HSSC-10
HSSC Chair Group Meeting: Monday 14 May, from 14:00
HSSC Plenary Meeting: Tuesday 15 to Thursday 17 May, noon
HSSC Chair Group Meeting: Thursday 17 May, from 14:00-17:00
Reports and Proposals by HSSC WGs:
  ppt presentation only (HSSC template)
  proposals (of possible strategic importance) that might need to go through the Council for endorsement
  proposals that might go directly to the IHO MS for approval through IHO CL
  key work items (top priorities), targets, risk/issues for 2019-20 IHO Work Programme, funding requirements…, that should be highlighted at C-2